## OA List
SL. | Application List | Department | Priority | Requested By | Benefits | Status | Progress Description | Progress % | Function | Developed by | Start Date | End Date | Days | Delivery Date
01 | Cutting & Marking | Production | High | Production/Akram | Improved precision and efficiency in production processes by monitoring and analyzing standard vs actual deviations in big cutting and marking, leading to better quality control and resource optimization. | WIP |  | 100% | Big Cutting Standard-Standard vs actual deviation Cutting Standard-Standard vs actual deviation Marking Standard-Standard vs actual deviation | Mostofa | 2024-03-19 | 2024-03-21 | 2 | Delivered
02 | Material Requisition -Extension | Production | High | Production/ Akram | Streamlined material requisition and return processes, ensuring efficient cross-checking and traceability for enhanced inventory control and resource utilization. | Pending |  |  | Material Module Return Material Checklist-File wise return material cross checking Material Requisition Slip/Book-Interdepartmental material requisition (Tape, ERP Memo Materials, Superglue) Return Material Form-File wise material return after completion for Not OK and KG(Hardware)/Pieces (Thread) Supplement Module Supplement Material Form (Hardware)Book-Preassembly to Cutting requisition Supplement Material Leather Book-Preassembly to Cutting requisition and Cutting to SCM | Mostofa | 2024-03-23 | 2024-04-01 | 9
03 | Procurement process | Procurement | High | SCM/Shurid | Streamlined procurement operations with an established process and supplier evaluation matrix, promoting efficient supplier selection and continuous improvement in procurement practices. | WIP |  | 90% | procurement process to established & find new supplier evaluation matrix for rating by CFT team. | Mostofa | 2024-04-02 | 2024-04-08 | 6
04 | Budget Extension | Accounts | High | Accounts / Jwel | Streamlined budget processes with yearly automation for initial submissions and monthly adjustments, improving efficiency and accuracy in financial management. | Pending |  | 70% | Yearly Budget Automation Department will submit the budget ones in a year Monthly Budget Adjustment Automation Monthly Budget and cost adjustment based on existing account head. | Mostofa | 2024-04-09 | 2024-04-14 | 5
05 | SI & SO system | IA/IT | High | IA / Sarwar | Service order and indent processes, improving efficiency, accuracy, and communication for seamless service delivery. | Pending |  |  | Services order and services indent like as PI & PO | Mostofa | 2024-04-16 | 2024-04-28 | 12
06 | TMIS Section wise Input Hours | IE | High | IE/Mamun | We have line wise Efficiency calculation for production floor, Now we are measure every line section wise efficiency calculation, So we get more details information | Completed |  | 100% | Section Wise efficiency calculation | Mostofa | 2024-04-30 | 2024-05-01 | 1 | Delivered
07 | TMIS Section wise Output Appsheet | IE | High | IE/Mamun | We have line wise Efficiency calculation for production floor, Now we are measure every line section wise efficiency calculation, So we get more details information | Completed |  | 100% | Section Wise efficiency calculation | Mostofa | 2024-05-02 | 2024-05-06 | 4 | Delivered
08 | Carton Weight confirmation | Packing | High | Packing/Sumon | Esily we can see how many carton weight confirm as PO wise amd make report visualization | WIP |  | 100% | Verify packing accuracy before handing goods to the warehouse, ensuring correct CTN packing and keeping weight record | Mostofa | 2024-05-07 | 2024-05-11 | 4 | Delivered
09 | Hourly Quality Status | QC | High | QC/Ajay | Real-time monitoring and control of production quality through hourly checks, defect tracking, and visualized reports, ensuring proactive quality management. | Pending |  | 0% | IPQC Painting Report 1.Hourly bag Check qty & Defect Qty. (Shoulder) 2. Top 3 Defect like ( Paint stain, Paint missing, Paint bubble, Paint unsmooth, Paint press mark) Overhead Paint Manual Report 1.Painting report on overhead area 2. Bag check qty, Defect Qty 3. Top 3 issues are visualized Work Process Audit sheet 1.Work with top defect of previous month. PQC Hourly Report 1.Every hour PQC check FQC pass bag & found how many defect write down on this report. |  | 2024-05-12 | 2024-05-25 | 13
10 | Documentation Management | Admin | Medium | Admin/Ahad | Streamlined license tracking and efficient visualization of audit reports in the VLMBD (Visual License Management and Business Documents), optimizing documentation processes for enhanced compliance and accessibility | Pending |  |  | License updating tracking File, Audit report visualization in the VLMBD | Mostofa | 2024-05-25 | 2024-05-30 | 5
11 | PC Tools Inventory | Production | Medium | Production/Akram | Efficient tracking and management of production-specific internal assets, reducing loss, damage, and streamlining the return process. | Pending |  |  | Production ID wise internal asset inventory (lost, damage, return records) | Mostofa | 2024-05-30 | 2024-06-02 | 3
12 | Machine & Tools Repair Requisition | Production | Medium | Production/Akram | Streamlined and efficient process for managing repair requests, ensuring prompt approvals and facilitating seamless transitions from production to Total Productive Maintenance (TPM). | Pending |  |  | Repair approval or move to disposal Production to TPM | Mostofa | 2024-06-03 | 2024-06-10 | 7
13 | QCO PCD schedule confirmation and sharing | PC | Medium | PC/Azad | Streamlined and efficient confirmation of Production Control Division (PCD) schedules through the 4M (Man, Machine, Material, Method) approach, facilitating clear communication and coordination in the production process. | Pending |  |  | PCD schedule confirmation though 4M ensuring. | Mostofa | 2024-06-11 | 2024-06-16 | 5
14 | Early shipment confirmation | PC | Medium | PC/Azad | Streamlined logistics with timely confirmation of goods readiness, enabling efficient workshop planning and ensuring adherence to production schedules | Pending |  |  | Goods early ready as per PC plan, so need workshop confirmation. | Mostofa | 2024-06-17 | 2024-06-22 | 5
15 | Extension Request | PC | Medium | PC/Azad | Streamlined and efficient processing of extension requests in response to abnormal situations such as low output, material issues, or quality concerns, leading to improved project management and timely resolution of challenges. | Pending |  |  | due to abnormality( low output, Materials issue/Quality issue), extension request. | Mostofa | 2024-06-23 | 2024-06-29 | 6
16 | Ex-factory Change Request | PC | Medium | PC/Azad | Streamlined response to abnormalities in production, materials, or quality issues, optimizing the change request process for efficient and timely resolutions. | Pending |  |  | due to abnormality( low output, Materials issue/Quality issue), Ex factory change request. | Mostofa | 2024-06-30 | 2024-07-04 | 4
17 | E workshop bag hour/final settlement data | PC | Medium | PC/Azad | Streamlined and efficient billing confirmation process for workshop services, leading to faster and more accurate financial settlements. | Pending |  |  | E workshop billing confirmation | Mostofa | 2024-07-05 | 2024-07-10 | 5
18 | ESS- Extension | HCM | Medium | HCM/Atiq | Streamlined performance evaluations with the Monthly Evaluation Form, facilitating efficient annual increment processes. Mobile Pass feature enhances real-time tracking of employee accessibility on production floors, ensuring efficient monitoring. Online management of disciplinary actions, warnings, and separation letters simplifies record-keeping and compliance with legal requirements. Automation of Annual Increment Letters provides easy access to increment data, ensuring transparency and adherence to legal guidelines. Requisition Form and Disciplinary Action Portal in ESS facilitate employee needs and internal complaint management, promoting a systematic approach. Empowers employees to correct attendance records, manage group changes, and handle shift modifications, fostering flexibility and accuracy in workforce management. | WIP |  |  | Monthly evaluation form TM-ESS This is mandatory requirement to evaluate employees performance for their annual increment. Employee Performance Evaluation for Staff (Supervisor & Above) This is mandatory requirement to evaluate employees performance for their annual increment. Employee Promotion Assessment (Officer & Above) This is required to evaluate employees performance during promotion interview. Mobile Pass for TM-ESS This is required to track mobile accessibility of TM in production floors. Show Cause, Warning & Separation letter-ESS This is required to maintain disciplinary activities. This is mandatory requirements though we need to maintain hard copy of these documents but to track the record in a feasible way online version is required. Annual Increment Letter of TM-ESS To fulfil law guidance, we have to show all employees increment data at user end. Though we need to keep the hard copy of these document but the system automation is required. Requisition form-ESS Its required for employees needs, Manpower Budget Disciplinary Action Portal-ESS Internal Complain Management- Details sheet of incident scenario Disciplinary Action TM-WS- Proof of guilty and hard paper submission Disciplinary Action GL to above- Proof of guilty and hard paper submission Emp Shift & Attendance correction-ESS Group Change-Shift Change-Interdepartmental employee shifting. Punch Correction - Internal daily punch missing, layoff, correction, leave, absent, ML etc. Night Shift - Internal daily punch missing, layoff, correction, leave, absent, ML etc. | Mostofa | 2024-07-11 | 2024-08-10 | 30
19 | Security Management | Admin | Medium | Admin/Atiq | Enhanced security oversight through organized and automated checklists, registers, and reports, ensuring thorough monitoring and documentation of critical security aspects | Pending |  | 0% | Security CheckList: Fire Door Checklist, 9 Point Inspection Checklist, Perimeter Checklist Security Register: Parcel mail, Documents received & distribution Register, Security Accident & Incident Register, Electrical Off/On & Generator Off/On Register, Lost & Found Register, Security Duty register, Handover & Takeover Register (All Duty Post), Advance Information Shipment Record Register Kye Management system Register: Daily Key Issue/return/, Main Key Box Sealed Opened (Main Gate)/, Key Lost Replace (Main Gate), Others Security Patrolling (Ventura) report, Security Disciplinary action |  | 2024-08-11 | 2024-08-30 | 19
20 | CCTV Management System | Admin | Medium | Admin/Atiq | Improved surveillance efficiency with real-time monitoring, staff movement tracking, secure seal management, quick case investigations, and effective communication through the PA system | Pending |  | 0% | CCTV Staff Movement/Seal (pata) Lock maintain/Case Investigation/ PA System Announcement/Camera offline/online/Camera offline incident |  | 2024-08-31 | 2024-09-05 | 5
21 | Compliance training, Meeting Record ( Physical Signature ) | Admin | Medium | Admin/Atiq | Streamlined compliance training and meeting documentation with physical signatures for increased accountability and adherence to safety protocols. | Pending |  | 0% | Training & meeting documents, Fire, First aid, PPE, H&S PC, Canteen ,Fire Drill Others record |  | 2024-09-06 | 2024-09-16 | 10
22 | CNC Mold combination | IE | Medium | IE/Mamun | Record all the CNC mold combination and store for future reference | Pending |  | 0% |  |  | 2024-09-17 | 2024-09-27 | 10
23 | Equipment Requisition | IE | Medium | IE/Mamun | Proper record for equipment transaction record | Pending |  | 0% |  |  | 2024-09-28 | 2024-10-02 | 4
24 | 1st pcs Quality Audit | QC | Medium | QC/Ajay | Improved quality control with real-time inline audits, quick identification of abnormalities, and efficient documentation, ensuring consistent product quality | Pending |  | 0% | Inline Audit 1.Inline first finished bag comparison with GoBy / PP Sample related documents,trim card,File information. 2.If ok or found any abnormalities then insert on report QCO 1.During QCO first semi finished part pass or fail Qc Record by this report. Bag Measurement Sheet 1.When FQC pass 1st bag of any color any style QC measurement compare with bulk and CS sample |  | 2024-10-03 | 2024-10-06 | 3
25 | IQM Sheet （IQM报告） | QC | Medium | QC/Ajay | Rapid Quality Control (QC) integration into bulk production, enabling quick identification of defects in running style bags and facilitating timely corrective measures for improved production quality. | Pending |  | 0% | 1.At the time of bulk producton within 4hr QC along with production disccus and report about running style bags most possible defect and solutions |  | 2024-10-07 | 2024-10-11 | 4
26 | Quality Checklist | QC | Medium | QC/Ajay | Ensure 100% inspection of metal logos through a comprehensive Inline IPQC report. Facilitate meticulous quality control by checking for damages such as shoulder damage, loop damage, zipper, puller damage, handle damage, etc., enhancing product quality assurance. | Pending |  | 0% | Logo Check --IPQC logo 1.Through this report Inline IPQC make sure 100% check of metal logo. Functionality Check List 1.QC check damage function like as shoulder damage,loop damage,zipper & puller damage,Handle damage etc. |  | 2024-10-12 | 2024-10-17 | 5
27 | FGWH Out pass | QC | Medium | QC/Ajay | Streamlined and efficient process for rechecking and collecting bags/containers from the warehouse, improving overall workflow and reducing manual errors. | Pending |  | 0% | 1. For recheck ,Bag/CTN collectuion from WH |  | 2024-10-18 | 2024-10-22 | 4
28 | Tapestry Inline Report-- MK Inline Report | QC | Medium | QC/Ajay | Improved quality control with plant-wise PQC reports for better analysis and decision-making. Efficient tracking and resolution of defects and issues through detailed documentation, enhancing overall product quality. | Pending |  | 0% | 1.Plant wise PQC report 2.Defect,Issue details |  | 2024-10-23 | 2024-10-28 | 5
29 | Packing Module | Packing | Medium | Packing/Fazlul | Keep a record of all the packing statuses by file and style. | WIP |  | 20% | File Information Displays details about a file, such as its PO, Plant, Destination, Group, Style, Color, qty, etc. Packing list Carton/cardboard booking as per packing list UCC/case label create in packone system as per packing list, Plant wise qty distribution Weight information have in packing list, Carton size, CBM, Shipping mark, Carton list make based on packing list, Load plan make based on packing list Daily Packing status Share the file wise packing status Hourly Packing Report Integrating real-time data to provide production with a more precise view of their hourly performance. Report Packing Report for related dept. Packing status report for shipment followup schedule |  | 2024-10-28 | 2024-11-15 | 18
30 | Body material inspection and calculation report | IQC | Medium | IQC/Shurid | Streamlined record-keeping and efficient calculation of body material inspections, facilitating accurate and comprehensive reporting for quality control and analysis. | Pending |  | 0% | To keep record for body inspection & calculate the record summary |  | 2024-11-16 | 2024-11-20 | 4
31 | Hardware inspection & Transaction | IQC | Medium | IQC/Shurid | Streamlined tracking of transactions between IQC and Warehouse, optimizing inventory management and ensuring efficient hardware inspection processes. | Pending |  | 0% | Track down the transaction between IQC & Warehouse and Report |  | 2024-11-21 | 2024-11-27 | 6
32 | Sub Contact Automation | Purchase | Medium | Purchase/Shurid | Subcontractor management by tracking and centralizing all relevant history, including Purchase Orders, Goods Received Notes, and Payment Applications, providing comprehensive oversight and efficiency. | Pending |  | 0% | Track down subcontract all history. i.e PI, PO, GRN, Payment application etc. |  | 2024-11-28 | 2024-12-15 | 17
33 | QR label order | WH | Medium | WH/Shurid | Streamlined and efficient QR label requisition process with real-time tracking, reducing manual errors and improving order management. | Pending |  | 0% | QR label requisition receive,send, approval. Data source ERP- Appsheet |  | 2024-12-16 | 2024-12-20 | 4
34 | Recruitment Module | HCM | Medium | HCM/Atiq | Streamlined and efficient recruitment processes with an online platform, reducing manual effort, minimizing errors, and ensuring compliance with legal requirements. | Pending |  | 0% | Offer letter (Staff) At present we are doing this manually for each selected candidate which is very much time consuming and sometimes it creates error. To reduce the time and improve accuracy we need an online platform for this process. Employee Information form (Staff) At present we are providing a word file to each selected candidate asking them fill the form and send back to us on mentioned time. Which is very difficult for the candidate and also for us to manage and compile the data as it is time consuming and possibility of errors. Thats why we need an online platform. Employee Nominee Form As this form is mandatory as per law guidance though we need to have an online version of this form to maintain accuracy and preserve the record. Appointment letter (Staff) As this is mandatory as per law guidance though we need to have an online version of this form to maintain accuracy and preserve the record. |  | 2024-12-21 | 2024-12-28 | 7
35 | QCO Module | Production | Medium | Production/Akram | Streamlined quality control operations with detailed records, accurate deviation analysis, and efficient pre/post-QCO checklists, ensuring enhanced production quality and performance. | Pending |  | 0% | QCO Downtime - All interdepartmental direct downtime record sheet with acknowledgement QCO IE Accuracy - Standard vs actual deviation according to provided layout QCO External Support & RFT - All interdepartmental OTD and RFT calculation based on pre-selected parameter QCO Metrics - QCO result calculation based on hourly output QCO TPM Accuracy - Standard vs actual deviation according to provided layout through machine lists, initial setup QCO PE Accuracy - Standard vs actual deviation according to mold, pattern list Pre-QCO A3 Checklist - Basic checklist for every QCO for signing acknowledgement Post-QCO - Basic checklist after every QCO for interdepartmental performance Pre-QCO Meeting Checklist - (-3) days and (-1) days QCO preparation checklist QCO Sequential Accuracy - IE accuracy performance in assembly area for N/N/N styles CNC Pre-QCO - for CNC area all interdepartmental QCO checklist before (-8 & -4 days) QCO Production Pilot Score Card - Hard paper for production pilot score card with written major findings |  | 2024-12-29 | 2025-02-15 | 48
36 | Execution Report | Production | Medium | Production/Akram | Improved operational efficiency with real-time monitoring of daily floor and line activities, enabling timely decision-making and performance optimization. | Pending |  | 0% | Daily all floor and line working standard monitoring |  | 2025-02-16 | 2025-02-21 | 5
37 | Compliance Report | Production | Medium | Production/Akram | Efficient tracking of compliance issues, facilitating timely monitoring, reporting, and adherence to regulatory requirements | Pending |  | 0% | Align with compliance issues for checking and monitoring |  | 2025-02-22 | 2025-02-28 | 6
38 | Material Transaction | Production | Medium | Production/Akram | Streamlined material inventory management with automated tracking and control, optimizing internal input and output processes for increased efficiency. Improved monitoring of overhead painting input and output, as well as hourly output, enhancing overall workflow and productivity. | Pending |  | 0% | Automation Material Inventory - Internal input & output tracking and control Overhead Painting Input Output Book - Internal input & output tracking and control Hourly Output Monitoring Book - TM workstation to workstation workflow/ one section to another section |  | 2025-03-01 | 2025-03-10 | 9
39 | Leather Color Rework Book | Production | Medium | Production/Akram | Streamlined color spray approval process, improving communication and efficiency within the CSC department for leather rework. | Pending |  | 0% | Color spray approval to CSC department |  | 2025-03-11 | 2025-03-21 | 10
40 | Internal S6S Report | Production | Low | Production/Akram | Streamlined daily internal S6S audit processes, ensuring systematic and efficient monitoring of key parameters for enhanced organizational lean compliance and safety. | Pending |  |  | Daily internal S6S audit parameters checking | Mostofa | 2025-03-22 | 2025-03-27 | 5
41 | LHL Daily Input & Acknowledgement | Production | Low | Production/ Akram | Streamlined communication and collaboration across departments through daily input and acknowledgment, improving efficiency and accountability | Pending |  |  | Daily interdepartmental acknowledgement and code confirmation status | Mostofa | 2025-03-28 | 2025-04-06 | 9
42 | Fire Safety Management | Admin | Low | Admin/Atiq | Improved fire safety compliance and readiness with streamlined and systematic monitoring of fire extinguishers, emergency lights, exit lights, and smoke detectors through checklists. | Pending |  | 0% | Fire Extinguisher/Emergency Light/ Exit Light/Smoke Detector Checklist |  | 2025-04-07 | 2025-04-14 | 7
43 | TMIS Feedback | IE | Low | IE/Mamun | Take feedback regarding TMIS from user | Pending |  | 0% |  |  | 2025-04-15 | 2025-04-18 | 3
44 | Quality Question Print 考试 | QC | Low | QC/Ajay | keep record Quality training and performance evaluation question and answer | Pending |  | 0% |  |  | 2025-04-19 | 2025-04-26 | 7
45 | Finish Goods Monitoring | Packing | Low | Packing/Fazlul | Streamlined and real-time tracking of finished goods from production to shipment, ensuring accurate confirmation, quality inspection, and efficient warehouse management for enhanced supply chain visibility. | Pending |  | 0% | Daily shipment confirmation On day shipment confirmation by logistics FG QA final inspection FG Warehouse Before final loading marking the cartons |  | 2025-04-27 | 2025-05-04 | 7
46 | Packing Information Sharing | Packing | Low | Packing/Fazlul | Streamlined communication and coordination between production, logistics, and teams, ensuring timely sharing of goods ready dates, VSL/RSD information, and invoice/cut-off dates for efficient tracking and delivery management. | Pending |  | 0% | Provide goods ready date PC team share goods ready date VSL/RSD and weekly based on Line, PO, style and color Invoice & Cut off date Logistics share Cut off date and Invoice based on VSL/RSD to tracks and follow up on delivery |  | 2025-05-05 | 2025-05-15 | 10
47 | KPI of Leather Team | IQC | Low | IQC/Shurid | Tracking and analysis of daily tasks for the Leather Team, facilitating efficient performance evaluation and strategic decision-making. | Pending |  | 0% | To keep record of daily tasks after that input in online |  | 2025-05-16 | 2025-05-21 | 5
48 | Leather Inspection and calculation summary | IQC | Low | IQC/Shurid | Streamlined leather inspection process with accurate record-keeping and automated calculation summaries, improving efficiency and reducing manual errors. | Pending |  | 0% | To keep record for leather inspection & calculate the record summary |  | 2025-05-22 | 2025-05-29 | 7
49 | Follow up Chart in VLMBD | Purchase | Low | Purchase/Shurid | Streamlined and efficient tracking of Purchase Order (PO) issuance and material movement, optimizing supply chain management for both local and overseas materials. | Pending |  | 0% | Tracking data for PO issue to inhouse the all materials(local & overseas) |  | 2025-05-30 | 2025-06-06 | 7
50 | ERP Memo App | WH | Low | WH/Shurid | Streamlined and efficient communication within the organization by facilitating web-based requisition processes, integrating seamlessly with ERP data sources for enhanced collaboration and decision-making | Pending |  | 0% | Webbing requisition receive,send, approval. Data source ERP |  | 2025-06-07 | 2025-06-13 | 6
51 | Zipper, Piping, Packing App | WH | Low | WH/Shurid | Streamlined production process with efficient tracking and recording of cut piece zipper, piping, and webbing, improving workflow transparency and inventory management. | Pending |  | 0% | Cut piece zipper, piping, webbing sending to WH record into VLMBD-Two form use |  | 2025-06-14 | 2025-06-23 | 9
52 | Chemical Consumption | WH | Low | WH/Shurid | Efficient tracking of chemical usage on a floor-by-floor basis, optimizing inventory management and promoting cost-effective resource allocation | Pending |  | 0% | Floorwise chemical sending record- |  | 2025-06-24 | 2025-07-04 | 10
53 | Exam question of TM | HCM | Low | HCM/Atiq | Streamlined TM recruitment process with an online platform, ensuring easy access, efficient exam administration, and secure result management for future reference. | Pending |  | 0% | During TM recruitment inititally we have to take exam. Once they passed the exam successfully we will go for next steps process. At present we are doing this using google form but it shows difficulties that’s why we need an online platform for easy access and also to manage and preserve the results for future reference. |  | 2025-07-05 | 2025-07-09 | 4
54 | Helper report | Production | Low | Production/Akram | Improved operational efficiency by implementing line and workstation-specific checklists for helper-designated tasks, ensuring systematic and accountable machine operation checks. | Pending |  | 0% | Line and workstation wise helper designated TM machine operation check list |  | 2025-07-10 | 2025-07-13 | 3
55 | Floor Closing Flow Chart | Production | Low | Production/Akram | Streamlined operations with a visual flow chart for efficient floor closing procedures, including real-time monitoring of electrical machinery status during lunch and after floor close for enhanced safety and energy conservation. | Pending |  | 0% | 2 times (during lunch and after floor close) all electrical machineries on/off status |  | 2025-07-14 | 2025-07-19 | 5
56 | Skill Matrix | Production | Low | Production/Akram | Improved workforce management with real-time skill identification, visualizations, and balanced utilization, leading to enhanced productivity and resource optimization. | Pending |  | 0% | Skill Matrix Flow chart - TM current skill identification and visualization Skill Inventory Flow chart - TM work balance and proper utilization based on their current wages TM Utilization Flow chart - TM work balance and proper utilization based on their current wages |  | 2025-07-20 | 2025-08-31 | 42
57 | File Sharing Apps with Scan | Merchandising | Low | Merch/Ruman |  | Pending |  |  |  |  | 2025-09-01 | 2025-09-15 | 14
58 | SRF | Merchandising | Low | Merch/Ruman |  | Pending |  |  |  |  | 2025-09-16 | 2025-09-22 | 6
59 | Internal Complain Management | Production | High | Production/Akram |  | WIP |  | 100% |  |  |  |  | 0 | Delivered
60 | Disciplinary Action TM-WS | Production | High | Production/Akram |  | Pending | [6 empty] | 0
61 | Disciplinary Action GL to above | Production | High | Production/Akram |  | Pending | [6 empty] | 0
62 | Group Change-Shift Change | HCM |  | HCM/Atiq |  | Completed |  | 100% | As this is mandatory as per law guidance though we need to have an online version of this form to maintain accuracy and preserve the record. | Mostofa |  |  | 0 | Delivered
63 | TM ID card | HCM |  | HCM/Atiq |  | Completed |  | 100% | As this is mandatory as per law guidance though we need to have an online version of this form to maintain accuracy and preserve the record. | Mostofa |  |  | 0 | Delivered
64 | Employees personal information update | HCM |  | HCM/Atiq |  | Completed |  | 100% | Required to update employees personal information when required. | Mostofa |  |  | 0 | Delivered
65 | Employee Job Card | HCM |  | HCM/Atiq |  | Completed |  | 100% | 1. Anytime employees can get their job card for any of their external or internal uses. | Mostofa |  |  | 0 | Delivered
66 | Confirmation & Increment letter (Staff) | HCM |  | HCM/Atiq |  | Completed |  | 100% | Yearly increment letter to distribute & keep record in employee file. | Mostofa |  |  | 0 | Delivered
67 | Pay slip | HCM |  | HCM/Atiq |  | Completed |  | 100% | To fulfil law guidance, we have to show the pay slip to all employees pay slip at user end. | Mostofa |  |  | 0 | Delivered
68 | Employee engagement survey TM | HCM |  | HCM/Atiq |  | Completed |  | 100% | Previously we are doing this by providing hard copy documents to all TM but after implement the portal it is easier for us to track the record. | Mostofa |  |  | 0 | Delivered
69 | Carton list | Packing |  | Packing/Sumon |  | Completed |  | 100% | To pack each CTN in line and generate the packing reports. | Mostofa |  |  | 0 | Delivered
70 | Finish Goods handover to WH | Packing |  | Packing/Sumon |  | Completed |  | 100% | FG transfer to WH and received from WH. Transaction between department and approval. | Mostofa |  |  | 0 | Delivered
71 | Employee Gate pass System | Admin |  | Admin/Ahad |  | Completed |  | 100% | Automatic tracking of employee IN-Out records within office hours. | Mostofa |  |  | 0 | Delivered
72 | Guest management System | Admin |  | Admin/Ahad |  | Completed |  | 100% | Automatic tracking of guest IN-Out records | Mostofa |  |  | 0 | Delivered
73 | vehicle management system | Admin |  | Admin/Ahad |  | Completed |  | 100% | Automatic tracking of vehicle IN-Out records | Mostofa |  |  | 0 | Delivered
74 | Invoice Receive App | Admin |  | Admin/Ahad | Streamlined and efficient material verification and receipt process, ensuring accuracy and accountability through individual item checks and electronic signatures. | Completed |  | 100% | Material checking one by one, material receiving from IQC and keep record E-Signature | Mostofa |  |  | 0 | 2024-02-25
75 | OT Management | Production | High | Production/Akram | Streamlined overtime approval process, improving efficiency and accountability. Real-time tracking of actual vs approved manpower count, optimizing resource management and cost control. | Completed | This application fully modified totally new requirements expense another 7days | 100% | OT Approval - Taking approval from PC Department OT Count Report - Actual vs approval manpower count on daily basis | Mostofa |  |  | 0 | 2024-02-27
76 | Sample material Requisition | Merchandising | High | Merch/Ruman | Streamlined and efficient material verification and receipt process, ensuring accuracy and accountability through individual item checks and electronic signatures. | Completed |  | 100% | Easily can do send Material requisition based on consumption rate | Mostofa |  |  | 0 | Delivered
77 | Sample material PI | Merchandising | High | Merch/Ruman | Streamlined and efficient material verification and receipt process, ensuring accuracy and accountability through individual item checks and electronic signatures. | Completed |  | 100% | Fully automated PI bulk upload by excel | Mostofa |  |  | 0 | Delivered

## Summary (hidden)
Priority | Count of Application List | Department | Count of Application List
High | 9 | Accounts | 1
Low | 17 | Admin | 5
Medium | 30 | HCM | 3
Grand Total | 56 | IA | 1
|  | IE | 5
|  | IQC | 4
|  | Packing | 3
|  | Packing | 1
|  | PC | 5
|  | Procurement | 1
|  | Production | 14
|  | Purchase | 2
|  | QC | 7
|  | WH | 4
|  | Grand Total | 56
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## GanttChart
Office Automation
Ventura Leatherware Mfy. (BD) Ltd. |  |  |  |  | Display Week | 8
|  |  |  | Progress Status | Not Start | 53
Project Start Date | 2024-03-01 |  |  |  | WIP | 3 | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
Project Lead | Hemel |  |  |  | Complete | 21 | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03
 | time axis 2024-04-15 to 2024-06-09
OA | Priority | PREDECESSOR | START | END | DAYS | % DONE | time axis 2024-04-15 to 2024-06-09
Application List |  |  |  | -
Cutting & Marking | High |  | 2024-03-19 | 2024-03-20 | 2 | 100%
Material Requisition -Extension | High |  | 2024-03-23 | 2024-03-31 | 9 | 0%
Procurement process | High |  | 2024-04-02 | 2024-04-07 | 6 | 90%
Budget Extension | High |  | 2024-04-09 | 2024-04-13 | 5 | 70%
SI & SO system | High |  | 2024-04-16 | 2024-04-27 | 12 | 0%
TMIS Section wise Input Hours | High |  | 2024-04-30 | 2024-04-30 | 1 | 100%
TMIS Section wise Output Appsheet | High |  | 2024-05-02 | 2024-05-05 | 4 | 100%
Carton Weight confirmation | High |  | 2024-05-07 | 2024-05-10 | 4 | 100%
Hourly Quality Status | High |  | 2024-05-12 | 2024-05-24 | 13 | 0%
Documentation Management | Medium |  | 2024-05-25 | 2024-05-29 | 5 | 0%
PC Tools Inventory | Medium |  | 2024-05-30 | 2024-06-01 | 3 | 0%
Machine & Tools Repair Requisition | Medium |  | 2024-06-03 | 2024-06-09 | 7 | 0%
QCO PCD schedule confirmation and sharing | Medium |  | 2024-06-11 | 2024-06-15 | 5 | 0%
Early shipment confirmation | Medium |  | 2024-06-17 | 2024-06-21 | 5 | 0%
Extension Request | Medium |  | 2024-06-23 | 2024-06-28 | 6 | 0%
Ex-factory Change Request | Medium |  | 2024-06-30 | 2024-07-03 | 4 | 0%
E workshop bag hour/final settlement data | Medium |  | 2024-07-05 | 2024-07-09 | 5 | 0%
ESS- Extension | Medium |  | 2024-07-11 | 2024-08-09 | 30 | 0%
Security Management | Medium |  | 2024-08-11 | 2024-08-29 | 19 | 0%
CCTV Management System | Medium |  | 2024-08-31 | 2024-09-04 | 5 | 0%
Compliance training, Meeting Record ( Physical Signature ) | Medium |  | 2024-09-06 | 2024-09-15 | 10 | 0%
CNC Mold combination | Medium |  | 2024-09-17 | 2024-09-26 | 10 | 0%
Equipment Requisition | Medium |  | 2024-09-28 | 2024-10-01 | 4 | 0%
1st pcs Quality Audit | Medium |  | 2024-10-03 | 2024-10-05 | 3 | 0%
IQM Sheet （IQM报告） | Medium |  | 2024-10-07 | 2024-10-10 | 4 | 0%
Quality Checklist | Medium |  | 2024-10-12 | 2024-10-16 | 5 | 0%
FGWH Out pass | Medium |  | 2024-10-18 | 2024-10-21 | 4 | 0%
Tapestry Inline Report-- MK Inline Report | Medium |  | 2024-10-23 | 2024-10-27 | 5 | 0%
Packing Module | Medium |  | 2024-10-28 | 2024-11-14 | 18 | 20%
Body material inspection and calculation report | Medium |  | 2024-11-16 | 2024-11-19 | 4 | 0%
Hardware inspection & Transaction | Medium |  | 2024-11-21 | 2024-11-26 | 6 | 0%
Sub Contact Automation | Medium |  | 2024-11-28 | 2024-12-14 | 17 | 0%
QR label order | Medium |  | 2024-12-16 | 2024-12-19 | 4 | 0%
Recruitment Module | Medium |  | 2024-12-21 | 2024-12-27 | 7 | 0%
QCO Module | Medium |  | 2024-12-29 | 2025-02-14 | 48 | 0%
Execution Report | Medium |  | 2025-02-16 | 2025-02-20 | 5 | 0%
Compliance Report | Medium |  | 2025-02-22 | 2025-02-27 | 6 | 0%
Material Transaction | Medium |  | 2025-03-01 | 2025-03-09 | 9 | 0%
Leather Color Rework Book | Medium |  | 2025-03-11 | 2025-03-20 | 10 | 0%
Internal S6S Report | Low |  | 2025-03-22 | 2025-03-26 | 5 | 0%
LHL Daily Input & Acknowledgement | Low |  | 2025-03-28 | 2025-04-05 | 9 | 0%
Fire Safety Management | Low |  | 2025-04-07 | 2025-04-13 | 7 | 0%
TMIS Feedback | Low |  | 2025-04-15 | 2025-04-17 | 3 | 0%
Quality Question Print 考试 | Low |  | 2025-04-19 | 2025-04-25 | 7 | 0%
Finish Goods Monitoring | Low |  | 2025-04-27 | 2025-05-03 | 7 | 0%
Packing Information Sharing | Low |  | 2025-05-05 | 2025-05-14 | 10 | 0%
KPI of Leather Team | Low |  | 2025-05-16 | 2025-05-20 | 5 | 0%
Leather Inspection and calculation summary | Low |  | 2025-05-22 | 2025-05-28 | 7 | 0%
Follow up Chart in VLMBD | Low |  | 2025-05-30 | 2025-06-05 | 7 | 0%
ERP Memo App | Low |  | 2025-06-07 | 2025-06-12 | 6 | 0%
Zipper, Piping, Packing App | Low |  | 2025-06-14 | 2025-06-22 | 9 | 0%
Chemical Consumption | Low |  | 2025-06-24 | 2025-07-03 | 10 | 0%
Exam question of TM | Low |  | 2025-07-05 | 2025-07-08 | 4 | 0%
Helper report | Low |  | 2025-07-10 | 2025-07-12 | 3 | 0%
Floor Closing Flow Chart | Low |  | 2025-07-14 | 2025-07-18 | 5 | 0%
Skill Matrix | Low |  | 2025-07-20 | 2025-08-30 | 42 | 0%
File Sharing Apps with Scan | Low |  | 2025-09-01 | 2025-09-14 | 14 | 0%
SRF | Low |  | 2025-09-16 | 2025-09-21 | 6 | 0%
Internal Complain Management | High |  | 0 | 0 | 0 | 100%
Disciplinary Action TM-WS | High |  | 0 | 0 | 0 | 0%
Disciplinary Action GL to above | High |  | 0 | 0 | 0 | 0%
Group Change-Shift Change | 0 |  | 0 | 0 | 0 | 100%
TM ID card | 0 |  | 0 | 0 | 0 | 100%
Employees personal information update | 0 |  | 0 | 0 | 0 | 100%
Employee Job Card | 0 |  | 0 | 0 | 0 | 100%
Confirmation & Increment letter (Staff) | 0 |  | 0 | 0 | 0 | 100%
Pay slip | 0 |  | 0 | 0 | 0 | 100%
Employee engagement survey TM | 0 |  | 0 | 0 | 0 | 100%
Carton list | 0 |  | 0 | 0 | 0 | 100%
Finish Goods handover to WH | 0 |  | 0 | 0 | 0 | 100%
Employee Gate pass System | 0 |  | 0 | 0 | 0 | 100%
Guest management System | 0 |  | 0 | 0 | 0 | 100%
vehicle management system | 0 |  | 0 | 0 | 0 | 100%
Invoice Receive App | 0 |  | 0 | 0 | 0 | 100%
OT Management | High |  | 0 | 0 | 0 | 100%
Sample material Requisition | High |  | 0 | 0 | 0 | 100%
Sample material PI | High |  | 0 | 0 | 0 | 100%