## Work List
S/N | Dept | Project Name | Sub Project/Work List | Lead by | Work Type | PROGRESS % | START | END | DAYS | YES if Main Project | Remarks
1 | IA | Hoshin Kanri | Hoshin Kanri | Sarwar | Yearly | 20% | 2024-01-25 | 2024-01-30 | 6 | Yes | Urgent
2 | IA | Hoshin Kanri | Hoshin Kanri score finalization | Sarwar | Yearly | 100% | 2025-01-25 | 2024-01-30 | -360
3 | IA | Hoshin Kanri | 1st Quarter, 24 Meeting | Sarwar | Yearly | 0% | 2024-04-04 | 2024-04-15 | 12
4 | IA | Hoshin Kanri | 2nd Quarter, 24 Meeting | Sarwar | Yearly | 0% | 2024-07-04 | 2024-07-15 | 12
5 | IA | Hoshin Kanri | 3rd Quarter, 24 Meeting | Sarwar | Yearly | 0% | 2024-10-04 | 2024-10-15 | 12
6 | IA | Hoshin Kanri | 4th Quarter, 24 Meeting | Sarwar | Yearly | 0% | 2025-01-04 | 2025-01-15 | 12
7
8 | IA | Policy Management | Policy Management | Sarwar | Project | 33.33% | 2024-01-10 | 2024-07-06 | 179 | Yes
9 | IA | Policy Management | Reviewing Meeting with Admin | Sarwar | Project | 100% | 2024-01-10 | 2024-01-30 | 21
10 | IA | Policy Management | Reviewing Meeting with HCM | Sarwar | Project | 0% | 2024-04-04 | 2024-04-15 | 12
11 | IA | Policy Management | Reviewing Meeting with TPM | Sarwar | Project | 0% | 2024-05-04 | 2024-05-04 | 1
12 | IA | Policy Management | Reviewing Meeting with F&A | Sarwar | Project | 0% | 2024-06-05 | 2024-06-05 | 1
13 | IA | Policy Management | Reviewing Meeting with Production | Sarwar | Project | 0% | 2024-07-06 | 2024-07-06 | 1
14 | IA | Policy Management | Reviewing Meeting with IM | Sarwar | Project | 100% | 2024-02-01 | 2024-04-02 | 62
15
16 | IA | HOD Meeting | HOD Meeting | Sarwar | Monthly | 8.333% | 2024-01-01 | 2024-12-31 | 366 | Yes
17 | IA | HOD Meeting | Monthly meeting, Jan 2024 | Sarwar | Monthly | 100% | 2024-01-27 | 2024-01-27 | 1
18 | IA | HOD Meeting | Monthly meeting, Feb 2024 | Sarwar | Monthly | 0% | 2024-02-27 | 2024-02-27 | 1
19 | IA | HOD Meeting | Monthly meeting, Mar 2024 | Sarwar | Monthly | 0% | 2024-03-27 | 2024-03-27 | 1
20 | IA | HOD Meeting | Monthly meeting, Apr 2024 | Sarwar | Monthly | 0% | 2024-04-27 | 2024-04-27 | 1
21 | IA | HOD Meeting | Monthly meeting, May 2024 | Sarwar | Monthly | 0% | 2024-05-27 | 2024-05-27 | 1
22 | IA | HOD Meeting | Monthly meeting, Jun 2024 | Sarwar | Monthly | 0% | 2024-06-27 | 2024-06-27 | 1
23 | IA | HOD Meeting | Monthly meeting, Jul 2024 | Sarwar | Monthly | 0% | 2024-07-27 | 2024-07-27 | 1
24 | IA | HOD Meeting | Monthly meeting, Aug 2024 | Sarwar | Monthly | 0% | 2024-08-27 | 2024-08-27 | 1
25 | IA | HOD Meeting | Monthly meeting, Sep 2024 | Sarwar | Monthly | 0% | 2024-09-27 | 2024-09-27 | 1
26 | IA | HOD Meeting | Monthly meeting, Oct 2024 | Sarwar | Monthly | 0% | 2024-10-27 | 2024-10-27 | 1
27 | IA | HOD Meeting | Monthly meeting, Nov 2024 | Sarwar | Monthly | 0% | 2024-11-27 | 2024-11-27 | 1
28 | IA | HOD Meeting | Monthly meeting, Dec 2024 | Sarwar | Monthly | 0% | 2024-12-27 | 2024-12-27 | 1
29
30 | Black Belt | Color belts training | Color belts training | Sarwar | Project | 20% | 2024-02-15 | 2024-12-15 | 305 | Yes
31 | Black Belt | Production Re-engineering | Production Re-engineering | Sarwar | Project | 0% | 2024-02-24 | 2024-10-15 | 235 | Yes
32 | Black Belt | Kaizen program | Kaizen program | Sarwar | Project | 80% | 2024-02-05 | 2024-12-29 | 329 | Yes
33 | Black Belt | Six Sigma deployment projects | Six Sigma deployment projects | Sarwar | Project | 100% | 2024-06-23 | 2024-12-23 | 184 | Yes
34 | IA | Power bi Dashboard Review | Power bi Dashboard Review | Sarwar | Project | 30% | 2024-02-15 | 2024-03-30 | 45 | Yes
35 | IA | Power bi Dashboard Review | Review with HCM & Admin | Sarwar | Project | 30% | 2024-02-15 | 2024-02-15
36 | IA | Power bi Dashboard Review | Review with IM | Sarwar | Project | 30% | 2024-02-28 | 2024-02-28
37 | IA | Power bi Dashboard Review | Review with Production | Sarwar | Project | 30% | 2024-03-15 | 2024-03-15
38 | IA | Power bi Dashboard Review | Review with SCM | Sarwar | Project | 30% | 2024-03-20 | 2024-03-20
39 | IA | Power bi Dashboard Review | Review with TPM | Sarwar | Project | 30% | 2024-03-30 | 2024-03-30
40
41 | Black Belt | S6S Audit | S6S Audit | Sarwar | Quarterly | 25% | 2024-01-28 | 2024-02-29 | 33 | Yes
42 | Black Belt | S6S Audit | 1st Quarter, 24 Audit | Sarwar | Quarterly | 100% | 2024-04-04 | 2024-04-15 | 12
43 | Black Belt | S6S Audit | 2nd Quarter, 24 Audit | Sarwar | Quarterly | 0% | 2024-07-04 | 2024-07-15 | 12
44 | Black Belt | S6S Audit | 3rd Quarter, 24 Audit | Sarwar | Quarterly | 0% | 2024-10-04 | 2024-10-15 | 12
45 | Black Belt | S6S Audit | 4th Quarter, 24 Audit | Sarwar | Quarterly | 0% | 2025-01-04 | 2025-01-15 | 12
46
47 | Production | Project 1_Prod | Project 1_Prod | Akram | Project | 90% | 2024-01-28 | 2024-02-29 | 33 | Yes
48 | IT | Project 1_IT | Project 1_IT | Hemel | Project | 60% | 2024-01-28 | 2024-02-15 | 19 | Yes
49 | Quality | Project 1_Q | Project 1_Q | Hemel | Project | 90% | 2024-01-28 | 2024-02-29 | 33 | Yes
50 | Merchandising | Project 1_Mer | Project 1_Mer | Ruman | Project | 60% | 2024-01-28 | 2024-02-20 | 24 | Yes
51 | Admin | Project 1_Admin | Project 1_Admin | Atiq | Project | 100% | 2024-01-28 | 2024-02-29 | 33 | Yes
52 | F&A | Project 2_F&A | Project 1_Admin | Atiq | Monthly | 100% | 2023-01-28 | 2023-02-28 | 32 | Yes
53 | Production | Project 2_Prod | Project 1_Prod | Akram | Project | 90% | 2024-01-28 | 2024-02-29 | 33 | Yes
52 | HCM | Project 1_HCM | Project 1_HCM | Atiq | Project | 60% | 2024-01-30 | 2024-02-22 | 24 | Yes
53 | SCM | Project 1_SCM | Project 1_SCM | Shurid | Project | 90% | 2024-01-28 | 2024-02-29 | 33 | Yes
54 | TPM | Project 1_TPM | Project 1_TPM | Salauddin | Project | 0% | 2024-01-30 | 2024-02-22 | 24 | Yes
55 | PC | Project 1_PC | Project 1_PC | Azad | Project | 60% | 2024-01-30 | 2024-02-22 | 24 | Yes
56 | PE | Project 1_PE | Project 1_PE | Dipok | Project | 90% | 2024-01-29 | 2024-02-20 | 23 | Yes
57 | Packing | Project 1_Packing | Project 1_Packing | Sumon | Project | 0% | 2024-01-25 | 2024-02-29 | 36 | Yes
58 | Admin | 2nd Phase | 2nd Phase | Thomas | Project | 0% | 2024-02-02 | 2025-02-28 | 393 | Yes
59 | Admin | Compliance set up in E floor | Compliance st up in E floor | Thomas | Project | 50% | 2023-02-02 | 2024-12-28 | 696 | Yes
60 | SCM | New ERP Implementation | New ERP Implementation | Robert | Project | 0% | 2024-02-02 | 2024-07-29 | 179 | Yes
61 | Purchase | Project 1 | Project 1_Pur | Sophia | Project | 0% | 2024-02-02 | 2024-07-29 | Yes | Yes
62 | Shipping | Project 1 | Project 1_Shipping | Atrif | Project | 0% | 2024-02-02 | 2024-07-29 | Yes | Yes
63
64

## Sheet1 (hidden)
S/N | Dept | Project Name | Sub Project/Work List | Lead by | Work Type | PROGRESS % | START | END | DAYS | YES if Main Project | Remarks
S/N | Dept | Project Name | Sub Project/Work List | Lead by | Work Type | PROGRESS % | START | END | DAYS | YES if Main Project | Remarks

## Yearly Calendar_Sarwar
Human Capital Development Program Callender
Day | January | February | March | April | May | June | July | August | September | October | November | December
1 | WEEK 1 |  | Friday | 1.HOD Meeting 2.Yellow Belt Training 3.Blue Belt Training |  | WEEK 23 | 1. Blue Belt Training |  | WEEK 36 | 1.PBI Training- Basic 2. | Friday | WEEK 48
2 | 1. HOD Meeting-1 | Friday | WEEK 10 |  |  | 1. HOD Meeting 2. Blue Belt Training |  | Friday | 1.HOD Meeting 2. PBI Training- Advance |  | WEEK 44 | 1.HOD Meeting Certification 2.Handover program-YB.BB
3 |  | WEEK 6 | 1.HOD Meeting Yellow Belt Training |  | Friday |  |  | WEEK 32 |  |  | 1.HOD Meeting 2.PBI Training- Basic
4 |  | 1.HOD Meeting-2 2.6 Sigma Green Belt |  |  | WEEK 19 |  |  | 1.HOD Meeting 2. PBI Training- Advance |  | Friday
5 | Friday |  |  | Friday | 1.HOD Meeting 2.Yellow Belt Training 3. Blue Belt Training |  | Friday |  |  | WEEK 40
6 | WEEK 2 |  |  | WEEK 15 |  |  | WEEK 28 |  | Friday | 1.Kaizen Meeting 2.PBI Training- Advance |  | Friday
7 | 1. Kaizen Meeting |  |  | 1.Kaizen Meeting 2.Yellow Belt Training 3. Blue Belt Training |  | Friday | 1. Kaizen Meeting 2. Blue Belt Training 3. |  | WEEK 35 |  |  | WEEK 49
8 |  |  | Friday |  |  | WEEK 24 |  |  | 1.Kaizen Meeting 2. PBI Training- Basic |  | Friday | 1.Kaizen Meeting 2.PBI Training- Advance
9 |  | Friday | WEEK 11 |  |  | 1. Kaizen Meeting 2. Blue Belt Training |  | Friday |  |  | WEEK 45
10 |  | WEEK 7 | 1. Kaizen Meeting 2.Yellow Belt Training |  | Friday |  |  | WEEK 33 |  |  | 1.Kaizen Meeting 2.PBI Training- Advance
11 |  | 1.Kaizen Meeting 2. 3.6 Sigma Green Belt |  |  | WEEK 20 |  |  | 1.Kaizen Meeting 2. PBI Training- Basic |  | Friday
12 | Friday |  |  | Friday | 1. Kaizen Meeting 2.Yellow Belt Training 3.Blue Belt Training |  | Friday |  |  | WEEK 41
13 | WEEK 3 |  |  | WEEK 16 |  |  | WEEK 29 |  | Friday | 1.S6S Audit By Black Belts- TPM & Admin area 2. S6S Meeting 3.PBI Training- Basic |  | Friday
14 | 1. S6S Audit BY Blck Belt-SCM 2. S6S Meeting |  |  | 1.Yellow Belt Training 2.Blue Belt Training |  | Friday | 1.Blue Belt Training 2.S6S Audit By Black Belts- VGO 3.S6S Meeting 4. |  | WEEK 37 |  |  | WEEK 50
15 |  |  | Friday |  |  | WEEK 25 |  |  | 1. 2.PBI Training- Advance |  | Friday | 1.PBI Training- Basic
16 |  | Friday | WEEK 12 |  |  | 1.Blue Belt Training |  | Friday |  |  | WEEK 46
17 |  | WEEK 8 | 1.Blue Belt Training 2. Yellow Belt Training |  | Friday |  |  | WEEK 34 |  |  | 1. PBI Training- Basic
18 |  | 1.Yellow Belt Training 2. 3. |  |  | WEEK 21 |  |  | 1. PBI Training- Advance |  | Friday
19 | Friday |  |  | Friday | 1.Yellow Belt Training 2.Blue Belt Training |  | Friday |  |  | WEEK 42
20 | WEEK 4 |  |  | WEEK 17 |  |  | WEEK 30 |  | Friday | 1.PBI Training- Advance |  | Friday
21 | 1. 2. 6 Sigma Green Belt |  |  | 1.Yellow Belt Training 2.Blue Belt Training 3.S6S Audit By Black Belts- Production 4.S6S Meeting |  | Friday | 1.Blue Belt Training 2. |  | WEEK 38 |  |  | WEEK 51
22 |  |  | Friday |  |  | WEEK 26 |  |  | 1. 2. PBI Training- Basic |  | Friday | 1. PBI Training- Advance
23 |  | Friday | WEEK 13 |  |  | 1. Blue Belt Training 2. |  | Friday |  |  | WEEK 47
24 |  | WEEK 9 | 1.Yellow Belt Training 2.Blue Belt Training |  | Friday |  |  | WEEK 35 |  |  | 1.Program- Reward , Recognition (S6S,Kaizen) 2.
25 |  | 1.Yellow Belt Training 2. 3.6 Sigma Green Belt |  |  | WEEK 22 |  |  | 1. PBI Training- Basic |  | Friday
26 | Friday |  |  | Friday | 1.Yellow Belt Training 2.Blue Belt Training |  | Friday |  |  | WEEK 43
27 | WEEK 5 |  |  | WEEK 18 |  |  | WEEK 31 |  | Friday | 1. PBI Training- Basic |  | Friday
28 | 1.6 Sigma Green Belt |  |  | 1.Yellow Belt Training 2.Blue Belt Training |  | Friday | 1.Blue Belt Training 2. |  | WEEK 39 |  |  | WEEK 52
29 |  |  | Friday |  |  | WEEK 27 |  |  | 1.HOD Meeting |  | Friday | 1. PBI Training- Basic
30 |  |  | WEEK 14 |  |  | 1. HOD Meeting |  | Friday
31 |  |  |  |  | Friday

## S6S (hidden)
S/N | Dept. | Work Title | Lead by | Work Type | PROGRESS % | START | END | DAYS | Remarks
2 | IA | 1st Quarter, 24 Audit | Sarwar | #REF! | 0% | 2024-04-04 | 2024-04-15
3 | IA | 2nd Quarter, 24 Audit | Sarwar | #REF! | 0% | 2024-07-04 | 2024-07-15
4 | IA | 3rd Quarter, 24 Audit | Sarwar | #REF! | 0% | 2024-10-04 | 2024-10-15
5 | IA | 4th Quarter, 24 Audit | Sarwar | #REF! | 0% | 2025-01-04 | 2025-01-15

## PM (hidden)
S/N | Dept. | Work Title | Lead by | Work Type | PROGRESS % | START | END | DAYS | Remarks
1 | IA | Reviewing Meeting with Admin | Sarwar | Reviewing Meeting with Admin | 100% | 2024-01-10 | 2024-01-30 |  | Urgent
2 | IA | Reviewing Meeting with HCM | Sarwar | Reviewing Meeting with Admin | 0% | 2024-04-04 | 2024-04-15
3 | IA | Reviewing Meeting with TPM | Sarwar | Reviewing Meeting with Admin | 0% | 2024-05-04 | 2024-05-04
4 | IA | Reviewing Meeting with F&A | Sarwar | Reviewing Meeting with Admin | 0% | 2024-06-05 | 2024-06-05
5 | IA | Reviewing Meeting with Production | Sarwar | Reviewing Meeting with Admin | 0% | 2024-07-06 | 2024-07-06

## HK (hidden)
S/N | Dept. | Work Title | Lead by | Work Type | PROGRESS % | START | END | DAYS | Remarks
1 | IA | Hoshin Kanri score finalization | Sarwar | #REF! | 100% | 2024-01-10 | 2024-01-30 |  | Urgent
2 | IA | 1st Quarter, 24 Meeting | Sarwar | #REF! | 0% | 2024-04-04 | 2024-04-15
3 | IA | 2nd Quarter, 24 Meeting | Sarwar | #REF! | 0% | 2024-07-04 | 2024-07-15
4 | IA | 3rd Quarter, 24 Meeting | Sarwar | #REF! | 0% | 2024-10-04 | 2024-10-15
5 | IA | 4th Quarter, 24 Meeting | Sarwar | #REF! | 0% | 2025-01-04 | 2025-01-15